## Gap Analysis
Reporting Hierarchy — CPO Requirement Gap Analysis
AMP-2548 [Enhancement] Reporting Manager Visibility & Case Assignment vs CPO input requirements
Prepared by: Huyen (PO) · Date: 03/09/2026 · US status: Ready To Clarify (Sprint 13 — SSO + Hierarchy + SCB Migration + FEEL) · Sources: AMP-2548, AMP-3323, AMP-3231, ACP-226/227, ACP-258, ADIB-5651/6725/7172, live RAKBANK portal
Coverage summary | Covered | 0 | Partially covered | 3 | Not covered | 3
Ref | CPO Input Requirement | Description | Where AMP-2548 Covers It | Coverage | Gap & Feedback to BA | Priority
R1 | Staff sees own applications only | Sale code / staff ID user can view only the applications tagged to them on the Enquiry screens. | AC4: pre-filter matching the logged-in user's sale code / staff ID against the application's Assigned To, applied before all existing filters; IM005 empty state; AC6 applies it to Application Enquiry + Report Enquiry. | Partially covered | The filter is defined but has no data to run on: (1) no AC defines how a case gets Assigned To at origination — live portal has no such field anywhere (list, details, audit trail); (2) the user record has no Sale Code / Staff ID attribute (AC1 adds only Reporting Manager; ACP-258 has none) — the matching key is undefined. Add capture ACs + user-record field with uniqueness, maker/checker, audit. | P1
R2 | Manager sees team applications | Manager access: can view all applications tagged to the users under them. | AC1–AC3: Reporting Manager field on Add/Edit User, View Details, List of Users (+filter/search/export); AC5: recursive subtree traversal incl. manager's own cases; AC7: maker/checker on RM changes. | Partially covered | Hierarchy and traversal are written, but: Context of Business says 'direct reports' while AC5 says full recursive subtree and the mockup filename says '03-Level' — pin the depth rule once. RM lifecycle rules missing: cycle validation beyond self-assignment (A→B→A), deactivating/deleting a manager who has reports, and mid-flight RM change (cases move between teams retroactively). | P1
R3 | Case tagging basis — Staff ID or UTM | Decide the attribution key for tagging a case, considering the UTM concept (board 734) and ADIB's current sale/promo code usage. | Not addressed — the US assumes Assigned To already exists; no analysis of the UTM model (AMP-3323, UAT Validated) against this feature. | Not covered | Decision + recommendation: tag by STAFF ID (person-level). UTM identifies the link/owner, its Share model changes visibility dynamically, and non-UTM cases fall back to '{Channel} Direct' visible to all — breaking staff-only visibility. Use the ADIB pattern: staff code carried in UTM URL (salesagentCode, ADIB-6725) + QR/manual capture (ADIB-5651) + round-robin default (ADIB-7172). See sheet 'Staff ID vs UTM'. | P1
R4 | Ops / admin retain full visibility | Roles that process all applications (back-office, credit ops, admins) must keep access after the restriction is introduced. | Not addressed — every enquiry user is forced into the staff/manager filter; users with no assignments and no reports see IM005 everywhere. | Not covered | Add a 'View All Applications' permission (role-level, default off) — same pattern AMP-3323 used ('View All Application Sources'). Define which existing roles receive it at migration, otherwise the release is a visibility regression for operations. | P1
R5 | Unassigned & historical cases | Who sees applications with no staff tag; what happens to existing production data at go-live. | Not addressed — Impact Analysis only covers Maker/Checker queue. | Not covered | Two decisions needed: (1) new unattributed cases → round-robin auto-assign from a config table (ADIB-7172) or an explicit 'Unassigned' pool visible to managers/view-all; (2) go-live backfill of existing applications (no Assigned To today) — without it, staff and managers open empty screens on day one. | P2
R6 | Report Enquiry follows the same visibility | Reports and exported report data scoped to the staff's own cases / the manager's subtree. | AC6: Report Enquiry row with staff/manager scoping incl. export scope. | Partially covered | The scoping rule is written but the baseline references are broken: ACP-229 does not exist and ACP-228 is 'Application Enquiry – Audit Trail' (Cancelled). Report Enquiry is also absent from the live portal menu (Enquiry > Application Enquiry only). Point to the correct baseline story or descope and raise separately. | P2
Legend: Coverage — Blue = Covered · Yellow = Partially covered · Navy = Not covered. Priority — P1 = must close before Ready for Dev, P2 = must close before development completes. All statements verified against the referenced Jira tickets and live RAKBANK portal screenshots (02/09/2026).

## Staff ID vs UTM
Case Tagging Decision — Staff ID vs UTM
Which key should tag a case for visibility: the person (Staff ID / sale code) or the link (UTM)?
Assessment against the CPO requirement (person-level visibility: staff sees own, manager sees team) · UTM model per AMP-3323 (UAT Validated) & AMP-3231 / IH14
Dimension | Staff ID / Sale Code | UTM (AMP-3323 model) | Assessment
What it identifies | The individual sale staff who sourced / handles the case. | The marketing link (campaign) and its owner — the user who created the UTM. | Only Staff ID resolves to a person. UTM owner ≠ handling agent.
Granularity | Person-level — one code per staff, matches 'staff sees own cases'. | Link-level — one owner runs many UTMs; several staff can share one link. | CPO requirement is person-level → Staff ID.
Capture point | At origination: UTM URL parameter (salesagentCode), QR scan, manual code input, round-robin default. | Auto-captured from utm_id in the URL when the customer opens the link. | Complementary — the UTM URL is one carrier of the staff code (ADIB-6725).
Visibility model | Deterministic reporting line: staff → own cases; manager → reporting subtree. | Ownership + Share dialog (View/Edit, Everyone or specific users) — visibility changes whenever sharing changes. | The Share model conflicts with a fixed reporting-line rule — visibility would depend on ad-hoc sharing actions.
Unattributed cases | Round-robin default from a config table guarantees every case is tagged (ADIB-7172). | Falls back to '{Channel Name} Direct' — visible to ALL users with Enquiry access. | UTM fallback directly breaks 'staff sees own cases only'.
Build status | New build: capture ACs + Staff ID field on user record needed. | Already UAT Validated (AMP-3323) incl. utm_id in URL, Enquiry UTM Source column, view-all permissions. | Reuse the UTM infrastructure as a carrier and keep its analytics — do not repurpose it as the assignment key.
Fit to CPO requirement | Direct fit — person tag + Reporting Manager hierarchy gives staff/manager visibility exactly as required. | Indirect — shared and direct cases would be visible to the wrong audience; owner-based, not line-based. | Staff ID wins on every visibility dimension.
RECOMMENDATION — Tag the case with STAFF ID (sale code). Capture it through four channels so every case is tagged: (1) UTM link parameter salesagentCode for digital journeys, (2) QR code scan, (3) manual code input for assisted journeys, (4) round-robin default from a configurable table when nothing is provided — the proven ADIB pattern (ADIB-6725, ADIB-5651, ADIB-7172). Keep UTM for campaign analytics only. The Reporting Manager hierarchy (AMP-2548) then determines who sees whose cases.

## ADIB Reference
ADIB Reference — Sale / Promo Code Usage Today
How ADIB tags every application to a staff code — the pattern to reuse for SMBP Reporting Hierarchy
All rows verified from the ADIB Jira project on 03/09/2026
# | Mechanism | How it works in ADIB | Ticket | Status | Reuse for SMBP Bank Portal
1 | Staff referral via QR scan | Customer scans the staff's QR during the journey; QR decrypts Branch Code, DSU Region, Source Code and Staff Referral Code. Every scan attempt (success/failure) is stored in a Referral table with timestamp; the latest successful code wins and is written to the Application table at submission. | ADIB-5651 | Open (HF enhancement) | Same capture pattern for branch-assisted journeys: store every capture attempt + the final tag on the application record.
2 | Manual staff code input | Customer types the staff referral code ('Enter code or scan QR'); code is validated in real time; valid codes follow the same storage rules as QR. Customer can re-enter until Confirm. | ADIB-5651 | Open (HF enhancement) | Fallback capture when there is no QR and no UTM link.
3 | Staff code inside the UTM link | UTM URL carries partnerCode + salesagentCode as parameters alongside utm_source/medium/campaign; values are stored on the Application table, shown in Super Portal application details, and written as the first audit-trail entry ('UTM Sourced application'). | ADIB-6725 | ADIB Dev Validated | Digital journeys: embed the staff code in the UTM URL — UTM analytics and staff tagging coexist on one link.
4 | Round-robin default (DSA / IFE) | If no code arrives via input, QR or UTM, the system assigns the next active IFE code from a DB config table (IFE_CODE, SEQUENCE_ORDER, LAST_ASSIGNED_FLAG, IS_ACTIVE) — configurable, no hardcoding; newly added codes are prioritized once, then the sequence resumes. Assigned code is stored on the Application table. | ADIB-7172 | ADIB Dev Validated | Guarantees every case carries a staff tag → nothing becomes invisible under staff/manager filtering.
5 | Audit trail for auto-assignment | Each round-robin assignment is recorded in the application's audit trail. | ADIB-7237 | ADIB Dev Validated | Keep an audit entry for every auto-assignment — needed for dispute handling and sales-credit disputes.
6 | Referral shown in the portal | The round-robin assigned referral is stored in 'Refer code' and displayed as staff referral in the Super Portal. | ADIB-7388 | UAT QC Validated | Display Assigned To / Sourced By on Application Details so managers can verify the tag.
7 | Staff referral report | A dedicated report on staff referral codes, built from the Application table using the latest successful code at submission. | ADIB-5651 (AC4) | Open (HF enhancement) | Per-staff performance reporting = the same data point that drives Report Enquiry scoping in AMP-2548.
Suggestion for SMBP: (1) add Sale Code / Staff ID to the Bank Portal user record and tag every application at origination via the four ADIB capture channels; (2) reuse the existing UTM engine as the digital carrier of the staff code instead of building a parallel mechanism; (3) make the default-assignment table configurable per channel with maker/checker, and audit every auto-assignment.